## Slide 1
Clean Hydrogen in European Cities
(256848)
Monika Kentzler
EvoBus GmbH
Notes: <number>

## Slide 2: 1. Project description and achievements CHIC objectives
The CHIC project will: implement clean urban mobility in 5 major European regions through the deployment of 26 hydrogen FC powered buses in medium sized fleets, and the enlargement of the hydrogen infrastructure systems
The CHIC project will: facilitate the development of clean urban public transport systems and mobility action plans into 14 new European regions
The CHIC project will: actively collaborate, transfer and secure significant key learning from previous FC projects into the CHIC stakeholders, thereby greatly accelerating the achievement of JTI and EC objectives
The CHIC project will: deliver greater community understanding of ‘green’ hydrogen powered FC buses, leading to increased political acceptance and commitment
Notes: <number>

## Slide 3: 1. Project description and achievements The CHIC concept
H2 Infrastructure and FCH Bus
Oslo
Aargau
Bolzano
Milan
London
Past
Present
Future
Dissemination
Phase 1
regions
Phase 2
regions
Phase 0
regions
Notes: <number>

## Slide 4: 1. Project description and achievements CHIC key facts
25 partners from 9 countries worldwide
( 10 transport companies, 8 industry partners and 7 research/consultants)
26 fuel cell buses operated in 5 Phase 1 cities; together with the Phase 0 cities more than 55 buses in operation
At least 3 different bus manufacturers in the Phase 1 cities
2 filling stations per Phase 1 city (one existing, one new station)
Demonstration phase 2010-2016
25.88 Mio. EUR funding, 81.8 Mio EUR costs
Notes: <number>

## Slide 5: 1. Project description and achievements technical goals of CHIC
Notes: <number>

## Slide 6: 1. Project description and achievements assessment of CHIC
  Performance assessment
    Monitoring of operation of H2 infrastructure and H2 buses
  Environmental assessment
    Environmental profile of the system, incl. LCA
    Land use and related impacts of fuel production
  Economic assessment
    Development/ enhancement of life cycle cost model covering H2 infrastructure and vehicles
    Target costing for benchmarking with other alternative buses
  Social acceptance
    Investigating the causative drivers behind different attitudes and perceptions of hydrogen powered public transport buses
Sustainability assessment of the use of hydrogen powered buses in public transport
Notes: <number>

## Slide 7: 1. Project description and achievements status of bus procurement / operation
 | City | No. of buses | Manu-facturer | Status of buses | Start of operation | km travelled (Aug. 31, 2011)
Phase 0 | Cologne | 2 | APTS | in service | April 2011 | 8.065
 | Hamburg | 7 | EvoBus | First 2 in service | August 2011 | 
 | Whistler | 20 | NewFlyer | in service | January 2010 | 850.000
Phase 1 | Aargau | 5 | EvoBus | Delivery: Oct. 2011 | n/a | n/a
 | Bolzano | 5 | Tbd | Tender to be re-published* | n/a | n/a
 | London | 8 | Wrightbus | First 5 in service, final 3 del. in Dec 11 | January 2011 | 57.400
 | Milan | 3 | EvoBus | Delivery: Dec. 2011 | n/a | n/a
 | Oslo | 5 | VanHool | Delivery: March 2012 | n/a | n/a
* due to internal budget discussions tender will most like only be re-published in Jan 2012
Notes: <number>

## Slide 8: Project description and achievements status of infrastructure procurement / operation of hydrogen refueling stations of Phase 1 cities
 | Phase 1 City | Source of hydrogen | Supplier | Status of station | Start of operation
1st (existing) station | Aargau | Not required | n/a | n/a | 
 | Bolzano | Delivered gaseous | Sapio (IT) | In operation (not for FC buses) | 
 | London | Delivered liquid | Air Products | In operation | 
 | Milan | Onsite reformer | Sol (IT) | Currently not operative | 
 | Oslo | Delivered gaseous | n/a | In operation (not for FC buses) | 
2nd station | Aargau | Onsite electrolyser + trailer delivery | Carbagas (Air Liquide) | Procured; building renovation started | April 2012
 | Bolzano* | Onsite electrolyser | tbd | Tender to be published end Sept 2011; awarding end Dec 2011 | End Dec 2012
 | London | High pressure tube trailer | Air Products | Design ongoing | July 2012 (before the Olympics)
 | Milan | Onsite electrolyser | Linde | Procured; construction to start Oct 2011 | End May 2012
 | Oslo | Onsite electrolyser | Air Liquide | Procured; construction to start in October; electrolyser delivery planned in Dec 2011 | March 2012
* 2nd refuelling station not financed through CHIC budget
Notes: <number>

## Slide 9: 1. Project description and achievements dissemination to Phase 2 cities
CHIC Hydrogen Refuelling Infrastructure Help-line:
Infraserv GmbH & Co. Höchst KG Tel. +49 69 305-17881
CHIC Fuel Cell Hydrogen Bus Help-line:
Element Energy
Tel. +44 (0) 330 119 0989 // +44 20 3195 8119
More than 25 cities are on the list of interested cities (so called Phase 2 cities).
A helpline has been created for cities that are interested in setting up new hydrogen bus projects.
First workshop to take place October 25th 2011 Busworld Europe Exhibition in Kortijk, Belgium with interested city representatives.
Notes: <number>

## Slide 10: 2. Alignment to MAIP/AIP Alignment to technical targets AIP 2009
Technical targets AIP (call 2009) | CHIC targets
Infrastructure: Capacity of 200 kg/day, upgradable to 100 vehicles per day Availability of station 98% OPEX < 10EUR/kg (excl. tax) Hydrogen purity and vehicle refueling time (according to SAE or analogous specification) Production efficiency target 50-70% | Infrastructure: Capacity of 200 kg/day, upgradeble to 100 vehicles per day Availability of station of 98% OPEX < 10EUR/kg (excl. tax) Hydrogen purity analogous SAE spec, bus refueling time not defined in SAE Production efficiency between 50-70% Replacement of 500.000 l diesel fuel
Buses: >4000h lifetime initially, min 6000 hrs lifetime as program target Availability >85% with maintenance as for conventional buses Fuel consumption < 11-13 kg/100km depending on drivecycle | Buses: Fuel cell lifetime > 6000 hrs Average availability of fuel cell buses > 85% Average fuel consumption < 13 kg/100km (depending on drive cycle) Minimum running distance of 2,75 Mio km of fleet Minimum of 160.000 hrs of operation of fleet
Notes: <number>

## Slide 11: 2. Alignment to MAIP/AIP Alignment to the technical targets of MAIP and potential improvements
  Target 2010: 20 buses on 3 sites with appropriate refueling infrastructure
Target could not be reached due to various reasons:
Start of JU FCH slower than expected
CHIC Grant Agreement only signed in November 2010
CHIC has started 4 new bus sites (Aargau, Bolzano, Milan, Oslo)
Further funding for the large demonstration projects with a demonstration start 2014/2015 are necessary to reach this target
Results of tendered commercialization study could update the figures
  Target 2015: 500 buses at 10 EU sites (of which at least 7 new
  ones) with refueling stations (daily capacity > 400kg)
Notes: <number>

## Slide 12
The dissemination and outreach is addressed by a separate work package, with two levels of dissemination:
3. Dissemination and Outreach
1. General dissemination
Internal Project Dissemination
Global Project Level engaging EU and international projects
Special Events: UITP Annual Conference, CIVITAS Annual Forum, EU Sustainable Energy Week, H2 & FC Fair, F-Cell Stuttgart
  2. Dissemination to Phase 2 cities to prepare for FCH powered bus integration in the near future
Engagement of local and regional transport authorities
Special Events: Busworld Europe, International Transport Forum
Notes: <number>

## Slide 13
Contacts to and collaborations with
  Very good cooperation within the project partners
  Visibility at EU energy and transport events (e.g. EP seminar, SET plan conference, EU future fuels group, European smart mobility innovations partnership)
  Most relevant organizations of local authorities( e.g. CONCERTO, CIVITAS, Covenant of Mayors, ACEA, UITP)
  International collaborations (e.g. International Fuel Cell Bus Workshop (US, Canada, Japan, China), IPHE recognition application, Clinton foundation)
  Collaboration with new JU FCH bus projects
CHIC 4. Enhancing cooperation and future perspectives
Notes: <number>

## Slide 14
Project Future Perspectives
  Due to the late signing of the CHIC Grant Agreement most buses will be delivered late in 2011, so that the demonstration on route will only begin in early 2012. This will have no effect on the overall project goals though as the project runs until December 2016.
  Commercialization study for fuel cell buses important for general future expectations of the technology
  Intensified cooperation between national and EU funding programs
CHIC 4. Enhancing cooperation and future perspectives
Notes: <number>