Clean Hydrogen In European Cities

Grant agreement No: 256848

Deliverable No. 4.3

<Report collecting the experience from the Phase 0 and Phase 1 cities with respect to certification of the buses & H2 refuelling infrastructure >

Status:D 
(D-Draft, FD-Final Draft, F-Final)

Dissemination level: PU

(PU – Public, PP – Restricted to other programme participants, RE – Restricted to a group specified by the consortium, CO – Confidential)

Authors:

Marieke Reijalt 
Eleni Seriatou

HyER Secretariat

Square de Meeus 1,

1000 Brussels,

Belgium

Author printed in bold is the contact person for this document.

Table of contents

0.	Executive Summary	6

0.1	The approach	7

0.2	Structure	8

A.	Hydrogen refuelling stations	9

1.	Stakeholders involved in the permitting process	9

2.	Laws and regulations applied	12

3.	Permits required	13

4.	Required information by authorities	15

5.	Target groups for safety assessment	16

6.	Technical standards used	17

7.	Methodologies and guidelines for the assessment of external (off-site) external effects damage and risks	18

8.	Inspection protocol	19

9.	Contingency planning	20

10.	Duration and costs of the approval process	21

B.	Certification of the buses	22

Conclusions:	23

List of abbreviations

ATEX			Potentially Explosive Atmospheres (“ATmosphères EXplosibles”)

FCH 			Fuel Cell Hydrogen

HRS			Hydrogen Refuelling Station

H2			Hydrogen

ISO			International Organization for Standardisation

# Executive Summary

The aim of this report is to collect the experiences from cities involved in the Clean Hydrogen In European Cities (CHIC) project on the authorisation procedures for hydrogen infrastructures and buses.

This report takes stock of the regulations described in previous EU projects, such as CUTE, HyFLEET:CUTE and HyApproval funded under the Sixth Framework Programme (FP6) and other information sources available to date and examines the current regulations applied at local level. Europe has already a draft regulation for compressed hydrogen refuelling stations developed in the frame of the EIHP project.

Based on these data collection, this report will serve as a basis for further input from industrial and officials to eventually contribute to the standardisation regulation in this technology.

With this first collection of experiences, the project will provide local authorities, companies and other stakeholders, including potentially interested Phase 2 Cities, with a reference document on the implementation and operation of hydrogen refuelling stations (HRS) as well as the operation of hydrogen fuel cell buses.

## The approach

Project partners from Phase 0 Cities and Phase 1 Cities (have been asked to indicate through a questionnaire the legislation and technical requirements that they fulfilled during the certification procedure of the Hydrogen Refuelling Stations (HRS). The scope of the survey is to assess the authorities involved in the permitting procedure, the diverse technical measures taken into account as well as the safety requirements which all vary significantly from country to country.

The second part of the questionnaire assessed the legislative procedures of acquiring and getting buses into operation.

In Phase O Cities (Hamburg, Cologne, Berlin and Whistler) partners had a longer experience in the installation and operation of the refuelling stations and buses.

The overall scope of the exercise is not only to examine the updates since the last codes and procedures on the topic but also to explore whether authorities are now more familiar than in 2008 on the technology.

The HyApproval Handbook for Approval of Hydrogen Refuelling Stations report, that covered 5 EU Member States (NL, FR, DE, IT, ES) and China, indicated that authorisation procedures could be time-consuming and sometimes required lengthy verification of the laws to apply and procedures to follow.

This report will explore if ISO drafts (i.e. 20100 “Gaseous hydrogen – Fuelling stations”) were already referred to in the approval processes and  if the time to obtain the licenses were in line with the authorisation procedures of comparable activities (industrial H2).

## Structure

On the one hand, the report takes a look at the refueling infrastructure and, in particular, the stakeholders involved in the issuing procedure, the laws and regulations applied, the permits acquired, the safety and technical standards, the methodologies for risks, the inspection protocol and the contingency planning, as well as the cost and the duration of the process.

On the other hand, the document examines if the EU regulation for the homologation of the buses was applied in all cities.

Respondents to this questionnaire include the following cities:

- Hamburg, (DE);

- Cologne,(DE);

- Whistler,(CA);

- Oslo, (NO);

- Aarau, (CH);

- London,(UK);

- Milan, (IT);

- Bolzano, (IT).

# Hydrogen refuelling stations

## Stakeholders involved in the permitting process

In Germany, project partners report that the authorities responsible for issuing permits vary significantly from district to district. In Hamburg and Cologne the regional authorities are issuing the permits. Inspection controls are performed by private agencies.

In Whistler, Canadian hydrogen installations must be constructed in conformance with appropriate municipal, territorial or provincial regulations, or in the absence of such regulations, in conformance with the requirements of the national model safety codes. Municipal local fire departments as well as local governments (for safety) are involved in the approval process in Canada.

On the other hand, in Italy and Oslo, the municipal and regional authorities along with the fire departments of each municipality are involved in the process. However, in Milan we note that different agencies are consulted to issue the permit.

In Aarau (Switzerland), in addition to the local authorities involved, the regional authority (the department of economic affairs and labour - Volkswirtschaft und Inneres –Wirtschaft und Arbeit – AWA) has to consent to the issue of a building license.

In the case of London, we note that additional safety controls were conducted in 2010, in view of the Olympic Games in 2012. In addition to these protocols, extra licenses were sought, as the building was located near a railway station.

| Role of Advisor | Name of organisation | Country/City |
| --- | --- | --- |
| Issuer of permit | Behörde für Soziales, Familie, Gesundheit und Verbraucherschutz (Ministry for Social and Family Affairs, Health and Consumer Protection)- Hamburg | DE |
| Advisor to issuer | Gewerbeaufsichtsamt bei der Reg. v. Oberbayern – München (Building Inspectorate in Upper Bavaria )- Munich |  |
| Inspection authority | Regierungspräsidium Darmstadt, Abt. Arbeitsschutz (Darmstadt Regional Council, Department of Labour Protection – Frankfurt), Frankfurt. |  |
| Issuer of permit | Behörde für Stadtentwicklung und Umwelt Hamburg (BSU) (Ministry of Urban Development and Environment) Hamburg - This varies from district to disctrict. For refueling station HafenCity the BSU was the responsible authority. | Hamburg |
| Inspection authority | TÜV Süd. The TÜV is not an authority but private. The TÜV inspects technically and the BSU controls if the TÜV has inspected. |  |
| Issuer of permit | Bauamt der Stadt Hürth, Bezirksregierung Köln (Building Authority of the City of Hurth, District Government of Cologne ) (Notification) | Cologne |
| Advisor to issuer | Bezirksregierung Köln (Cologne regional government) |  |
| Inspection authority | TÜV (see above). |  |
| Issuer of permit | Amt für Handel und Dienstleistungen der Autonomen Provinz Bozen – Südtirol (Office of trade and services of the Autonomous Province of Bozen – Südtirol) | IT (Bolzano) |
| Advisor to issuer | Dienststellenkonferenz der Gemeinde Bozen (Conferences of the Services of the municipality of Bolzano) |  |
| Advisor to issuer | Amt für Brandverhütung der Autonomen Provinz Bozen – Südtirol (Agency of Fire Prevention of the Autonomous Province of Bozen – Südtirol) |  |
| Provincial Fire Brigade Headquarter | Project assessment request Fire prevention certificate request Project assessment request Fire prevention certificate request | IT (Milan) |
| Milan municipality – Fuels office | Fuel station building authorization request Operation authorization request (In the authorization process are involved several agencies, like ASL, ARPA, ISPESL, INAIL, Milan Province, Lombardia Region, ENAC) |  |
| Milan municipality – Building office | Civil works authorisation request |  |
| Work health and safety office | Building works beginning notification |  |
| Formal notice | Oppegård municipality «Direktoratet for Sikkerhet og Berdskap» (Safety and Readiness) – This authority has not issued permit, but the builder and operator of the station had to give a formal notice. | NO (Oslo) |
| Advisor to issuer | “Direktoratet for sikkerhet og beredskap» Oslo og Follo Fire- department |  |
| Inspection authority | “Direktorat for sikkerhet og beredskap», the local fire – Departement. |  |
| Responsible for legislation | “Plan og byggningsloven” (law on building permits ) Several authorities amongst them Oppegård municipality “Brann og eksplosjonsvernsloven” ( law on fire and safety measurements) Several authorities, amongst them the local fire department, the local municipalities and « Direktoratet for sikkerhet og beredskap» |  |
|  | London Borough of Waltham Forest (Council) Olympic Delivery Authority London Organising Committee of the Olympic Games Fire Brigade Greater London Authority (Mayor of London’s office) Health and Safety Executive Network Rail (because the refuelling station was situated near a railway line) | UK (London) |
| Building licence | Stadtbauamt Brugg (building licence, in cooperation with the following authorities) | CH (Aarau) |
| Consent for a building licence operating approval | Aargaurische Gebäudeversicherung Brandschutz (Building fire insurance) |  |
| Consent for a building licence | Departement Volkswirtschaft und Inneres –Wirtschaft und Arbeit – AWA (The industrial and commercial supervision implements concerns of health and worker protection) |  |

## Laws and regulations applied

In Germany, the refuelling installations need a certificate according to the Federal Immission Protection Law (Bundes-Immissionsschutzgesetz, BimSchG, §13 BetrSichV (Betriebssicherheitsverordnung). Trucked-in stations can also apply for a normal operation permit according to the abovementioned law. Additional certification is required depending on the amount of hydrogen stored. Furthermore, in the case of stations with on-site production of hydrogen approval according to BimSchG is mandatory.

In Italy, both in Bolzano and Milan, the Ministerial Decree of 31 August 2006 was applied including fire prevention and local building rules.

In Oslo, similar regulations including building and safety aspects are applied, whereas in London the Control of Major Accident and Hazards (COMAH) regulations are applied. It is noteworthy that in Aarau several regulations on building and work safety are applicable (see table below).

| HRS’s are installations needing a certificate according to §13 BetrSichV (Betriebssicherheitsverordnung). Above 3 tons of stored hydrogen the Bundes-Immissions-Schutz –Gesetz (BimSchG, http://www.gesetze-im-internet.de/bimschg/) applies. Also the BimSchG applies if hydrogen is produced on-site for example via elctrolysis. Compare list of aggregates that need approval according to BimSchG in 4th BimSch-Verordnung (BimSchV) Column 1 point 4.1 section l) http://www.gesetze-im-internet.de/bimschv_4_1985/anhang_5.html If storing moren than 5 tons hydrogen the Störfallverordnung (Hazardous Incident Ordinance is applicable. http://www.gesetze-im-internet.de/bimschv_12_2000/anhang_i_30.html | DE (Cologne) |
| --- | --- |
| Decreto del Ministero (DM) dell’interno 31 agosto 2006 (Ministerial Decree of 31 August 2006) | IT (Bolzano) |
| Administrative laws: public contracts discipline D. LGS. 163/2006, public contracts code DPR 207/2010, work safety law D. LGS. 81/08 Approving laws: fire prevention DM 31/8/06, building local rules (Piano di Governo del Territorio), hygiene and environmental rules. | IT (Milan) |
| Plan og byggningsloven” (law on building permits “Brann og eksplosjonsvernsloven” with further Regulations (law on fire and safety measurements) | NO (Oslo) |
| Control of Major Accident and Hazards (COMAH) regulations. | UK (London) |
| EKAS - Eidgenössische Koordinationskommission für - Suva Arbeitssicherheit (job safty) | CH (Aarau) |
| Sonderfälle Entwässerung (Art. 12-15 GSchG §20 GSchG) |  |
| Störfallverordnung |  |
| AWA Plangenehmigung und Begutachtung inkl. AWA Beschreibungsformulare (Plan approval and inspection including AWA Description Forms) |  |
| ATEX - SUVA 2153, Explosionsschutz (exlposion prevention) |  |
| AGV Brandschutzbewilligung (fire protection) |  |

## Permits required

As explained in chapter 1 (“stakeholders involved in the permitting process”, c.f. p.9), similar permits are required in Milan and Bolzano, as building permits have to be provided by the municipality, whereas regional authorities are more responsible for the infrastructure operations (i.e. fire and safety permits). In Oslo, the municipality is held to issue a permit for the station installation, while official documentation on safety and operation aspects has to be provided to the authority.

The London Borough LB Waltham Forest grants a “Hazardous Substances Consent” to HRS applicants, whereas in Hamburg only one permit procedure is in place (the building permit provided by BSU). All relevant sub-authorities will be contacted by the BSU in this case. Within the BimSchG all relevant directives like the European pressure directive, TA Lärm (noise emission law in Germany), ATEX-check, operation of a filling station and others were also controlled.

| “Rammetillatelse” (not really a building permission – but a permission from Oppegård municipality to set up the hydrogen station and the structure around it). In addition one has to give the authorities a formal notice for safety and readiness. | NO (Oslo) |
| --- | --- |
| In Hamburg the BSU (regional authority) concentrates on the permit procedure in one permit procedure - the building permit. All relevant sub-authorities will be contacted by the BSU in this case. If you need an operation permit this will be integrated into this permit as well. For station HafenCity we needed at least the operational permit according to Betriebssicherheitsverordnung (BetriSiV) and as we are producing via electrolysis on-site also the BimSchG-approval. Within the BimSchG all relevant directives like European pressure directive, TA Lärm (noise emission law in Germany), ATEX-check, operation of a filling station etc were checked. | DE (Hamburg) |
| Planning permission (granted by LB Waltham Forest) Hazardous Substances Consent | UK (London) |
| See tables 1 and 2 | CH (Aarau) |
| See tables 1 and 2 | IT (Milan) |
| Building permits: Conferences of the Services of the municipality of Bolzano Environmental permit: Agency of Fire Prevention of the Autonomous Province of Bozen – Südtirol Operating permit: Office of trade and services of the Autonomous Province of Bozen – Südtirol | IT (Bolzano) |

## Required information by authorities

The information required by authorities varies from city to city. Namely, in Oslo detailed information on the hydrogen production and storage as well as the station installation is required. On the other hand, in London, the number of employees and the population in the surrounding area has to be reported. An exhaustive list of information covering safety and plant installation is required in Hamburg.

| Layout and placement of the station. How much gas will be produced/ stored. Information on how one will make sure that the station is safe and in compliance with the Norwegian legislation on safety. | NO (Oslo) |
| --- | --- |
| Employees, Population in the surrounding area | UK (London) |
| Depending on approval procedure. In case of BimSchG: Description of operational organisation. Technical drawings of station Wrap up of safety installations Foot print demand Area plans Description of building Description of Waste water system Description of rain water system Description of used aggregates in the station P&I drawings of station Description of ventilation system Description of used materials, dangerous goods Description of Feed in and output of materials Safety data sheets of all materials used Description of measures to avoid waste Description of measures how to dispose of waste Description of treatment of goods dangerous to water HAZOP analysis Description of rational use of energy Expertise on noise emissions Description of technical employment protection Safety expertise List of safety valves Greater list of alarm and control switches Additional safety expertise according to §29a BimSchG (not in every approval procedure. Authority CAN demand it but do not necessarily has to do it). Description of fire protection and gas warning installation Description of of lightning protection including report of installation Gas warning sensors and emergency shutdown plans Expert’s opinion of TÜV or other notified body on technical employment protection Explosion protection document Definition of EX-zones and zones with higher than normal oxygen concentration Ex-zone-plans Description of dangerous works Description of work with dangerous goods. Screening Document on environmental auditing. Description of measures in case of closure of operation | DE (Hamburg) |
| Civil works executive projects Plants definitive projects Current regulations requirements compliance declaration Fire risks assessment | IT (Milan) |
| At the moment not known | IT (Bolzano) |

## Target groups for safety assessment

Employees and operators are in focus within the safety assessment permits in all cities.

| Employees and operator | DE (Hamburg) |
| --- | --- |
| ATM employees, maintenance operators, buses refueling operators, depot guests | IT (Milan) |
| Agency of Fire Prevention of the Autonomous Province of Bozen – Südtirol | IT (Bolzano) |

## Technical standards used

All cities have applied the European Directive (ATEX) for plants in combination with other regulations for pressure equipment, while London has followed the European Industrial Gases Association standards (EIGA).

| Everything is built according to the various European EC Directives: • Machine Directive, • Pressure Equipment • Directive, ATEX Directive • EMC Directive • Etc. | NO (Oslo) |
| --- | --- |
| British Compressed Gas Association standards CP4,CP23 and CP33 European Industrial Gases Association standards (EIGA) 15-06, 100-03, 06-02E | UK (London) |
| ATEX - SUVA 2153, Explosionsschutz (explosion prevention) | CH (Aarau) |
| Reinforced concrete constructions regulations (NTC 2008), UNI, CEI, PED, ATEX plants regulations. | IT (Milan) |
| Decreto del Ministero (DM) dell’interno 31 agosto 2006 | IT (Bolzano) |
| Technical regulations in BetrSV (leading document) | DE (Cologne) |
| Regulations according to BimSchG and BimSchV (comrare above). Technical regulations in BetrSiVerordnung European Pressure Directive…. VdTÜV Merkblatt 514 § 3 BetrSichV § 4 BetrSichV TRG 400, 401, 402, 790 TRB 600, 610 TRBS 2141, 2152 All local laws (Hamburger Gesetze). (non-exhaustive enumeration) | DE (Hamburg) |

## Methodologies and guidelines for the assessment of external (off-site) external effects damage and risks

A qualitative and quantitative risk assessment is conducted in all cities focusing on the explosion prevention. HAZID (Hazard Identification Study) and HAZOP (Hazard and Operability Studies) methodology analysis take into account factors such as deviation, cause, effect and risk mitigation.

| The Operator Air Liquide will make regular safety inspection which will be protocolled The authority may carry out inspection if the feel the need for this. | NO (Oslo) |
| --- | --- |
| Air Products internal inspection procedure | UK (London) |
| Inspection protocol are made by the different authorities (see first point) | CH (Aarau) |
| The test procedure will be in three phases: - Empty plant - Plant filled with inert gas (Nitrogen) - Plant at full operation The whole test will be approved by TÜV and INAIL. | IT (Milan) |
| In the first three years of operation the supplier will perform the inspections according to the performance requirements of the tender. The first inspection will be done by the inspection authority. | IT (Bolzano) |
| According to BetrSichV every 5 years by Competent Safety Organisation. Tubes every half year by operators + manufacturers regulations. Also: 24 months after start-up and every three years. | DE (Cologne) |

## Inspection protocol

The hydrogen refuelling station supplier is performing the inspection control. In Aarau and in Italy inspection is subject to different local authorities.

| The Operator Air Liquide will make regular safety inspection which will be protocolled The authority may carry out inspection if the feel the need for this. | NO (Oslo) |
| --- | --- |
| Air Products internal inspection procedure | UK (London) |
| Inspection protocol are made by the different authorities (see first point) | CH (Aarau) |
| The test procedure will be in three phases: - Empty plant - Plant filled with inert gas (Nitrogen) - Plant at full operation The whole test will be approved by TÜV and INAIL. | IT (Milan) |
| In the first three years of operation the supplier will perform the inspections according to the performance requirements of the tender. The first inspection will be done by the inspection authority. | IT (Bolzano) |
| According to BetrSichV every 5 years by Competent Safety Organisation. Tubes every half year by operators + manufacturers regulations. Also: 24 months after start-up and every three years. | DE (Cologne) |

## Contingency planning

The station supplier is also conceiving and performing the contingency planning.

| Action plan of the fire brigade and firefighting - and safety plan. The project has involved all the authorities at an early stage. There will be carried out fire (safety) drills with the local fire department. | NO (Oslo) |
| --- | --- |
| An emergency response plan was drawn up. Air Products provided a 24-hour emergency hotline phone number. The station is fitted with CCTV and motion sensors and an emergency stop button. | UK (London) |
| Cooperation risk manager and fire department | CH (Aarau) |
| The emergency plan will be drawn up by Linde (the plant builder), on the base of the risks assessment performed at plant installation completed. | IT (Milan) |
| Not yet defined | IT (Bolzano) |
| Action plan of the fire brigade and safety response plan. Fire fighters or the agency for fire-prevention should be involved in an early stage as officials often want to have their point of view regarding emergency planning and access to the HRS. | DE (Cologne) |

## Duration and costs of the approval process

Hamburg, London and Italy report that the approval process takes approximately one year to complete. In the case of Milan, this is much longer than originally expected (i.e. 3 months), whereas in the case of London the organisation of the Olympic Games has added extra time to the whole process. Only London reports that approval costs were estimated around £50,000.

| Approx. one year excluding preparation of documents. In case of H2station HafenCity the BimSchG has been applied. The documents will also presented to the public for a certain amount of time and everyone could oppose to the project if good reasons are given. The publication of the documents needs to be communicated well ahead, the duration in which the documents are publicly available is set by law. | DE (Hamburg) |
| --- | --- |
| The approval process was very long and took over a year. This was mainly due to increased safety requirements imposed due to the Olympic Games 2012. We had to wait for approval until after the Olympic Authority had agreed what needed to be built in the nearby vicinity of our station. Costs were approximately £50,000. | UK (London) |
| The approval process has started in November 2011 and it’s still in progress; the initial approval process was calculated with only 3 months but now the duration foreseen is about 1 year. The costs of the approval process itself are not high. To get the approval the project ATM has to create additional detail drawings and several meetings with the different authorities and this are costs which you can add to approval costs. | IT (Milan) |
| Not yet known | IT (Bolzano) |

# Certification of the buses

The second part of the survey focused on the homologation of the buses in Phase 1 Cities.

Phase 1 Cities Bolzano, Milan and Oslo reported that the EU Regulation 406/2010 of 26 April 2010 implementing Regulation (EC) No 79/2009 of the European Parliament and of the Council on type-approval of hydrogen-powered motor vehicles was applied for the homologation of the buses.

Additional national regulations on road safety were also applied in Oslo.

However, in London the first 5 hydrogen vehicles were certified under ‘special order’ dispensation from UK’s Road Vehicles Regulations, whereas the 3 other vehicles were certified under the Individual Vehicle Approval 177879.

In Aarau, buses were homologated in compliance with the road safety regulations (Stva Strassenverkehrs- und Schiffsamt).

In Whistler, buses were homologated in compliance with SAE J2528 and 2529 as well as ISO standards 23273-1, 23273-2, and 23273-3.

Furthermore, final approval of the British Columbia Commercial Vehicle Safety Enforcement (CVSE) was required before the buses could be insured and put into service. CVSE also required that a third party engineering report be produced to verify that the buses were built to the specified standards

# Conclusions:

Analysis of the permitting processes and the issuing authorities in the partner cities shows similarities in terms of the authorities involved, and the permits issued.

The number of licences (building, infrastructure operations, environmental and safety permits) and the duration of approval processes vary slightly.

Licensing hydrogen refuelling infrastructure was an elaborate activity in HyFLEET:CUTE and HyApproval. The present exercise shows that issues identified in previous experiences have evolved since then in following way:

- Less disparities between regions and cities in terms of permits approval processes;

- International codes, regulations and standards have been applied.

CHIC city partners report that regional authorities are issuing permits relevant to the infrastructure operations, while civil works are under the supervision of local authorities. Furthermore, environmental and safety aspects in most cities fall under the responsibility of external agencies which are contracted to local authorities.

Although HyFLEET:CUTE and HyApproval assessed an absence of recognised codes of best practice and standards, this exercise shows that all cities used the same technical standards (EU regulations) in addition to their local regulations. The standardisation procedures should facilitate companies to invest in the technology and develop hydrogen infrastructure.

ISO TC197, particularly to WG11 “Gaseous hydrogen, ISO/DTS 20012

http://www.hyapproval.org/main1.html

http://www.h2fcc.ca/files/H2%20Permitting%20Guide%20-%20Rev.%204.1%20%5BEN%5D%20%2804.15.2008%29.pdf

Plan og byggningsloven” (law on building permits  “Brann og eksplosjonsvernsloven” with further Regulations (law on fire and safety measurements)